PROJECT PLAN  —  PROOF OF CONCEPT

AR Field Assistant with a

Self-Hosted LLM

A buildable proof-of-concept: DIY glasses + body-worn edge + private remote inference

Recommended arena:  Enterprise / industrial (hands-free maintenance & inspection assistant)

Scope:  Working POC — reparable and cost-effective over miniaturized or market-ready

Date:  June 2026      Indicative duration:  ~14–19 weeks (small team)

Tooling and model recommendations reflect the state of the art as of mid-2026 and will move quickly; treat specific models as swappable.

Contents

# 1.  Executive Summary

This plan turns the idea — an AR product powered by self-hosted LLMs — into a concrete, buildable proof-of-concept: do-it-yourself glasses driven by a body-worn single-board computer, talking over a mobile connection to open-weight models running on infrastructure you control.

Recommended arena. Of the three AR arenas, enterprise / industrial is the best fit for this hardware and hosting choice, and the strongest place to build a durable position. A body-worn compute pack is normal in industrial AR; the “repairable and cost-effective” ethos suits a POC; and “self-hosted but remote” inference maps directly onto how enterprises already prefer to keep data on their own private cloud or on-prem servers. It also sidesteps the two hardest paths — consumer miniaturization and social acceptability on one side, defense certification and air-gapping on the other — while keeping the door open to both later.

What we will build. A hands-free AI field assistant: a technician wearing the glasses can ask spoken questions and get answers grounded in the organization’s own manuals and procedures, point the camera at equipment and ask “what is this / what’s the next step / what looks wrong,” follow step-by-step guided procedures shown on the display, and capture notes or work-order fields by voice. The language/vision model is the brain and runs on your remote server; the wearable is deliberately a low-power, repairable input/output device.

Why self-hosting is the point. Running open-weight models on infrastructure you control means proprietary manuals, captured video, and worker data never leave your environment — the central advantage over a third-party cloud API, and a genuine moat in regulated and IP-sensitive industries. The plan treats privacy, data residency, and a private network tunnel as architecture, not afterthoughts.

Headline numbers. Roughly 14–19 weeks for a 2–4-person team; hardware capex on the order of US$1,200–$3,500 for one wearable unit plus a modest GPU server (less if you rent cloud GPU and tether to a phone). The single biggest risk is connectivity and latency, which the design mitigates throughout.

# 2.  Recommended Use Case & POC Scope

The POC is a hands-free maintenance / inspection / remote-expert assistant. Concrete capabilities, in priority order:

- Grounded voice Q&A. Ask a spoken question; get a concise answer drawn from your manuals/SOPs via retrieval (RAG), with source citations.

- Visual question answering. The camera sends what the worker sees to the vision-language model: “What part is this?”, “Is this assembled correctly?”, “What’s the next step?”

- Guided procedures. Step-by-step checklists rendered on the display, advanced hands-free by voice, with the model adapting to what the camera sees.

- Hands-free capture. Dictate notes or fill structured work-order fields by voice; the model formats and files them.

- Remote-expert call (stretch). Escalate to a human expert with shared live video when the assistant cannot resolve an issue.

Explicitly out of scope for the POC: miniaturization, industrial design, certification, multi-device fleet management, and on-device large-model inference. The goal is to prove the end-to-end experience and the self-hosted architecture, cheaply and reparably.

# 3.  System Architecture

Three wearable-side tiers plus a self-hosted remote brain, joined by a mobile link. Heavy reasoning lives on the server; the wearable handles capture, speech, display, and resilience.

Figure 1 — Three-tier wearable with self-hosted remote inference.

### Data flow, end to end

- Voice query: wake word → voice-activity detection → streaming speech-to-text on the edge → transcript (plus a recent camera keyframe, if relevant) sent over the tunnel → model retrieves from your manuals and answers → tokens stream back → edge renders text and speaks the reply, beginning before the full answer arrives.

- Visual query: the edge selects and compresses a keyframe → sends it with the question → the vision-language model reasons over the image → streamed answer + optional on-display annotations.

- Resilience: if the link drops, the edge falls back to cached procedures and on-device speech, queues actions, and resyncs when connectivity returns.

### Components

| Layer | Role | Key elements |
| --- | --- | --- |
| Head-worn glasses | Input / output only; low power | Display, camera, mic array, IMU, audio out |
| Body-worn edge (SBC) | Capture, speech, compositing, orchestration, resilience | Wake word, VAD, streaming ASR, TTS, session mgmt, cache/offline |
| Connectivity | Private link to the brain | 5G/LTE hotspot or USB modem; WireGuard VPN + TLS |
| Remote inference | Reasoning and knowledge | Open-weight VLM+LLM, RAG vector DB, agent/orchestration, auth, evals |
| Power | Independent, repairable | Separate USB-C PD battery packs for glasses and SBC |
| Enterprise systems | Source of truth | Manuals/SOPs (for RAG), work-order API |

# 4.  Technology Stack (state of the art, mid-2026)

Recommendations reflect the current open-weight landscape. Specific models move monthly — keep them swappable behind an OpenAI-compatible interface so you can upgrade without rework.

| Layer | Recommended | Alternatives | Why |
| --- | --- | --- | --- |
| Vision-language model | Qwen3-VL (e.g. 30B-A3B or a dense 7–8B), quantized | InternVL3, Llama 4 multimodal, Pixtral, Phi-4-multimodal | Strong open multimodal; FP8 builds; Apache-2.0 |
| Inference serving | vLLM or SGLang (OpenAI-compatible) | Ollama / llama.cpp (simplest early on) | Continuous batching, streaming, throughput |
| Quantization | FP8 or AWQ (server); GGUF for CPU/edge | GPTQ, INT8 | Fit a 24–48GB GPU; cut latency/cost |
| Retrieval (RAG) | Open embeddings + vector DB (Qdrant / pgvector) | Milvus, Weaviate; LlamaIndex for glue | Grounded answers with citations; data stays local |
| Speech-to-text (edge) | Moonshine v2 (Pi) / NVIDIA Nemotron-Streaming or Parakeet (Jetson) | Whisper Turbo / distil-whisper (multilingual) | Streaming, low-latency, on-device |
| Wake word + VAD | openWakeWord + Silero VAD | porcupine; WebRTC VAD | Cheap on-edge gating; fewer round-trips |
| Text-to-speech (edge) | Piper (offline, low-latency) | Kokoro, XTTS (server) | Fast spoken replies; works offline |
| Orchestration / agent | Thin FastAPI service + tool-calling | LangGraph (only if needed) | Avoid over-frameworking a POC |
| Observability / evals | Langfuse or Phoenix + a task eval set | Custom tracing | Evals are the steering wheel |
| Networking / security | WireGuard tunnel + TLS + token auth | Tailscale; mTLS | Private endpoint; data never public |

# 5.  Hardware Bill of Materials

Indicative mid-2026 prices for a single wearable unit plus one remote server. Reparability favored: off-the-shelf, modular, 3D-printed mounts.

| Component | Recommended option | Est. cost | Notes |
| --- | --- | --- | --- |
| Display / optical engine | Off-the-shelf display glasses driven as a monitor (XReal/Rokid/Viture class) | $200–$500 | Fastest, lowest-risk; swappable unit |
| — DIY alternative | Monocular micro-OLED module + combiner | $80–$200 | More “self-built”; higher effort |
| Edge SBC (primary) | Raspberry Pi 5 (8GB) + cooler + NVMe | ~$120 | Low power; LLM is remote, so no GPU needed |
| — SBC alternative | Jetson Orin Nano Super dev kit | ~$249 | On-edge GPU for offline fallback / local vision |
| Camera | USB UVC or Pi camera module | $25–$50 | Feeds the vision model |
| Microphone array | USB mic array (e.g. ReSpeaker) | $30–$70 | Far-field voice in noise |
| Audio out | Bone-conduction headset / earbuds | $20–$50 | Hands-free, ears-open |
| Connectivity | 5G/LTE hotspot or USB modem (or phone tether) | $0–$250 | Plus a data SIM; phone tether = $0 |
| Power | USB-C PD power bank(s) | $30–$80 | Separate packs; hot-swappable |
| Mounts / cables / harness | 3D-printed mounts, adapters, belt rig | $50–$120 | Repairable; documented |
| Remote GPU server | Own 24–48GB GPU (e.g. used RTX 3090/4090) or rent | $0–$2,000 | Rent = ~$0.5–$2/hr, no capex |

Indicative total: ~US$1,200–$3,500 for one unit + a modest owned GPU; substantially less if you rent the GPU hourly and tether to an existing phone.

# 6.  State-of-the-Art Techniques & Design Principles

### Latency is the product

A hands-free assistant feels broken if it waits, interrupts awkwardly, or misses the end of a thought. Hide latency aggressively: do wake-word, VAD, and end-pointing on the edge; stream tokens to the display as they generate and begin speaking partial replies; send compressed keyframes, not video; keep a persistent websocket/gRPC session; and cache frequent answers. Target first spoken token within ~1–2 seconds of the user finishing speaking.

### Right-size and quantize the model

Bigger is not better here. A quantized mid-size VLM (e.g. Qwen3-VL ~30B-A3B, or a dense 7–8B) served with vLLM/SGLang on a 24–48GB GPU gives strong multimodal quality at workable latency and cost. Reserve larger models for offline evaluation only.

### Ground every answer (RAG with citations)

Index the organization’s manuals and SOPs into a local vector database; retrieve relevant passages at query time and require the model to cite them. This is what makes answers trustworthy and domain-correct — and, because retrieval runs on your infrastructure, proprietary content never leaves it.

### Structured tool-calling and a tight agent loop

Use function-calling for actions (retrieve, file a work order, call an expert) with a small state machine for guided procedures and explicit confirmations before anything consequential. Resist heavyweight agent frameworks in a POC; a thin orchestrator is easier to debug and to make safe.

### Design for degraded and offline operation

Field connectivity is unreliable. Cache the active procedure and recent context on the edge, keep speech I/O working locally, queue captured data, and resync on reconnect. On a Jetson, a small local model can provide a basic offline fallback.

### Privacy and security by design

The wearable talks only to a private endpoint over a WireGuard tunnel with TLS and token auth; the model and all data live on infrastructure you control; captured imagery and PII are handled under a clear retention policy. This is the concrete realization of the self-hosting rationale.

### Evaluation-driven development

Stand up observability (request tracing) and a small evaluation set of representative tasks from day one. Track task-success rate, end-to-end latency (p50/p95), speech word-error-rate, and retrieval accuracy. Improve against the eval set, not vibes.

### Hands-free UX patterns

Glanceable, low-density display; clear “listening / thinking / speaking” states; voice + a single physical button for confirmation; never overload the visual field; fail safe and visibly when the link drops.

# 7.  Phased Delivery Plan

Sequencing principle: de-risk the AI brain before touching hardware. Prove model quality and the self-hosted stack against a laptop client first, then bring up the wearable, then layer in multimodal and workflows, then harden and field-test.

| Phase | Focus | Duration | Exit criteria |
| --- | --- | --- | --- |
| 0 — Foundations | Finalize use case & KPIs; procure hardware; stand up remote server; pick models; repo + observability | ~2 wks | Server serving a model via API; eval harness scaffolded |
| 1 — Remote brain | Serve VLM+LLM; build RAG over sample manuals; expose API; validate on a laptop client | 3–4 wks | Grounded Q&A + visual Q&A pass the eval set on a laptop |
| 2 — Edge bring-up | Assemble glasses + SBC + power + connectivity; display, camera, mic, audio; edge speech; end-to-end voice loop | 3–4 wks | Ask aloud, see/hear an answer over the network |
| 3 — Multimodal & workflows | Camera→VLM; guided procedures; hands-free capture; remote-expert call (stretch) | 3–4 wks | A full inspection task completed hands-free |
| 4 — Hardening & field test | Latency, offline fallback, battery/thermal, security (WireGuard/TLS/auth); real technician trial | 2–3 wks | KPIs met in a realistic field test |
| 5 — Evaluate & decide | Assess vs success criteria; document learnings; go/no-go + next steps | ~1 wk | Decision memo and recommendation |

Total: ~14–19 weeks. Phases 1 and 2 can partially overlap once hardware arrives, since the brain (Phase 1) is validated independently of the wearable.

# 8.  Workstreams & Team

A POC needs 2–4 people; roles can be combined for a leaner build.

| Role | Responsibilities | Allocation |
| --- | --- | --- |
| ML / LLM engineer | Model serving, quantization, RAG, agent loop, evals | Full-time |
| Embedded / edge engineer | SBC, Linux, audio/video I/O, speech pipeline, power, networking | Full-time |
| AR / UX (part-time) | Display UI, hands-free interaction, field ergonomics | ~0.5 |
| PM + domain SME (part-time) | Use case, content (manuals/SOPs), field test, KPIs | ~0.5 |

# 9.  Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Connectivity / latency in the field | High | High | Edge speech + streaming + keyframes + caching; offline fallback; set latency KPIs early |
| Battery life / thermal on the wearable | Med | Med | Separate hot-swappable packs; low-power SBC; offload heavy work to server |
| Display readability / ergonomics | Med | Med | Start with proven off-the-shelf optics; low-density glanceable UI; field test early |
| ASR accuracy in noise | Med | Med | Mic array + VAD; domain vocabulary; measure WER on representative audio |
| Model quality / hallucination | Med | High | RAG with citations; confirmations on actions; eval set; human-in-the-loop for stretch |
| Security of remote link | Low | High | WireGuard + TLS + token auth; private endpoint; retention policy |
| Hardware scope creep | Med | Med | Off-the-shelf first; POC, not product; freeze the BOM after Phase 0 |
| Hands-free safety | Low | Med | Confirmations for consequential steps; fail-safe on link loss; clear states |

# 10.  Success Criteria & KPIs

Illustrative targets — calibrate to your use case and environment during Phase 0.

| Metric | Target (illustrative) | How measured |
| --- | --- | --- |
| Voice query → first spoken token (p95) | < 2 s | Instrumented end-to-end traces |
| Task success rate (N representative tasks) | > 80% | Scored runs against an eval set |
| Speech word-error-rate (field audio) | < 10% | WER on representative recordings |
| Retrieval accuracy (answer cites correct source) | > 90% | Human review on eval set |
| Battery runtime (continuous use) | > 3 h | Field measurement |
| Technician usability | SUS > 70 / task completion | Field test survey + observation |
| Field-test uptime | > 95% of session | Session logs |

# 11.  Budget & Timeline Summary

- Timeline: ~14–19 weeks (~3.5–4.5 months) for a 2–4-person team.

- Hardware capex: ~US$1,200–$3,500 for one wearable unit + a modest owned GPU; near-zero capex if renting cloud GPU and tethering to a phone.

- Recurring: cloud GPU rental (if used, ~$0.5–$2/hr while running) and a data SIM; negligible if self-hosting on owned hardware in a homelab.

- Biggest cost lever: own vs. rent the GPU, and the display choice (off-the-shelf glasses vs. DIY optics).

# 12.  Next Steps & Decision Gate

At the end of Phase 5, assess the POC against the KPIs and decide go/no-go. If it works, the strategic question — from the market analysis — is which durable layer to own next: the assistant/workflow software (most defensible, and hardware-agnostic), a private-LLM deployment capability for regulated industries, or a productized field-service offering. The POC is deliberately structured so the durable value (the self-hosted model + RAG + workflow layer) is reusable regardless of which hardware path you ultimately choose, and regardless of whether you later move on-prem/air-gapped for regulated customers.

Immediate first actions (Week 1): confirm the target use case and a sample manual set with a domain SME; order the SBC, display unit, camera, mic, and battery; stand up the GPU server and serve a quantized VLM behind an OpenAI-compatible API; create the repo and observability; draft the eval task list.

# Appendix A.  Glossary & Key References

LLM / VLM — Large language model / vision-language model (accepts images + text). The POC’s “brain.”

Self-hosted — Running open-weight models on infrastructure you control (homelab, datacenter, or private cloud) rather than a third-party API.

RAG — Retrieval-augmented generation — grounding answers in your own documents, with citations.

ASR / TTS — Automatic speech recognition (speech→text) / text-to-speech (text→speech).

VAD / wake word — Voice-activity detection / a trigger phrase — on-edge gating to cut round-trips.

SBC — Single-board computer (Raspberry Pi 5, NVIDIA Jetson Orin Nano Super) — the body-worn edge.

Quantization — Compressing model weights (FP8, AWQ, GGUF) to fit smaller GPUs and reduce latency.

vLLM / SGLang / Ollama — Open inference servers; vLLM/SGLang for throughput, Ollama for simplicity.

WireGuard — A modern VPN; here, the private tunnel from the wearable to your inference server.

OpenXR / TAK — Open XR standard / military situational-awareness software (relevant if you later target defense).

Current-as-of-mid-2026 tooling referenced: Qwen3-VL and other open VLMs (InternVL3, Llama 4 multimodal, Pixtral, Phi-4-multimodal); serving via vLLM / SGLang / Ollama; edge ASR via Moonshine v2, NVIDIA Nemotron-Streaming, or Parakeet; TTS via Piper; SBCs Raspberry Pi 5 and Jetson Orin Nano Super. These are fast-moving — re-check before procurement and keep models swappable.